## Tabelle1
Date | Time Spent | Focus Area | Notes
2026-04-05 | 1.5 | UI Design (XAML) | Created initial UI blueprint. Sketched layout on paper and implemented main window structure in XAML (header, list area, action buttons).
2026-04-06 | 0.5 | Core class setup | Created core classes: GroceryItem, GroceryList, StoreLayout, Category. Defined basic properties and structure for future use.
2026-04-08 | 1.5 | AddItem window & Git setup | Created AddItem window (XAML). Implemented button to open AddItem Window. Connected project to GitHub repository. First push to GitHub.
2026-04-09 | 0.5 | Planning & Milestones definition | Created milestones document. defined weekly ddevelopment roadmap. Structured project into phases. Established clear development goals.
2026-04-10 | 4.5 | Core functionality implementation | Implemented core functionalities for AddItem Window, like Next Item, OK, Cancel, Select Category, Enter Text, Validation and bound to ListBox
2026-04-12 | 2 | UI polish & UX improvements | Improved layout alignment. Minor UI cleanup and spacing adjustments. final testing of full AddItem workflow. Category placeholder behavior.
2026-04-13 | 1.5 | Feature completion & UI refinement | Implemented Remove Item functionality (button + logic). Fixed layout alignment. Set window ResizeMode to prevent resizing.
2026-04-14 | 1.5 | ViewLists setup & data structure refactor | Implemented ViewLists window. Designed structured list preview UI. Nested data display. Refactored category handling. Temporary hardcoded lists.
2026-04-15 | 1.75 | CreateList feature & StoreLayout integration | Implemented CreateList window. Refactored: Replaced LayoutName with StoreLayout object. Connected selected layout to AddItem. Fixed binding issues + runtime crash.
2026-04-16 | 2 | CreateList validation & multiple list integration | Implemented Create List Validation & dynamic list creation into AllLists. Enabled multiple list support. Connected item addition within Creat List flow.
2026-04-17 | 1.5 | ViewLists buttons & layout alignment fix | Designed Select List and Delete List UI actions. Prepared functionality hooks. Fixed layout alignment issue using SharedSizeGroup.
2026-04-17 | 1.5 | List interaction & ViewLists navigation | Implemented Delete List functionality. Implemented Select List functionality. Added Back button to return to MainWindow. Added border layout for each list item.
2026-04-18 | 2.5 | Layout Handling & Manage Layouts Foundation | Detect layout change. Show confirmation warning and clear items on confirm. Built Manage Layouts window. Created Create Layout window. Basic layout & category creation
2026-04-19 | 2.75 | Layout Viewing & Category Management | Reordering categories with Up/Down buttons. Added Delete Category Button. Save created layouts. Displayed layout names in My Layouts. Warning messages for invalid moves.
2026-04-20 | 2.5 | Layout Integration, Editing & Validation | Layout binding to CreateList. Delete Layout. Prevent opening CreateList and AddItem without valid layout. Prevent duplicate layout and list names. Add Edit List & Layout functionality + buttons.
2026-04-22 | 1 | Core Sorting Logic | Implemented sorting function based on layout category order. Created sorted list without mutating original. Consider switching later to in-place sorting for better integration.
2026-04-22 | 0.5 | Sorting method refactor & UI Cleanup | Switched to returning ObservableCollection<GroceryItem> for better UI compatibility. Simplified Create List UI by removing unnecessary checkboxes.
2026-04-24 | 2 | INotifyPropertyChanged integration | Replaced most DataContext refresh hacks with proper INotifyPropertyChange. Fixed ManageLayouts resetting data by passing shared ObservableCollection.
2026-04-25 | 1.25 | Code cleanup & layout logic improvements | Removed Category class. Cleaned up old/unused code and comments. Implemented validation: layouts can only be deleted if no lists are using them. General refactoring.
2026-04-26 | 1.75 | UI polish & usability improvements | Adjusted button styling. Applied custom colors and overall visual theme. Improved layout formatting. Added basic UI refinements. General formatting of XAML and C# code.
2026-04-29 | 1.5 | UI fixes & database integration (start) | Fixed layout issues in ViewLists: fixed column widths, removed SharedSizeGroup. Began SQLite integration: Created database and tables, implemented LoadLayouts(), added Id property classes
2026-04-30 | 1.5 | Database persistence for layouts | Implemented SaveLayout() and DeleteLayout() methods. Updated delete validation to use Id instead of Name.
2026-05-01 | 1.25 | Database integration for grocery lists | Added Id property to remaining data classes. Implemented LoadLists(), LoadLayoutById(), LoadItemsForList(), SaveList(), DeleteList(), fulle connected database layer for lists and items.
2026-05-02 | 1.25 | Database Update Methods & Integration | Implemented UpdateLayout(), UpdateList(), UpdateItemChecked(). Added transaction handling for multi-step update operations. Connected checkbox changes to database updates.
2026-05-04 | 0.5 | App startup behavior | Implemented automatic loading of last created list on startup.
2025-05-11 | 2.25 | Edit functionality & UI polish | Implemented edit item and edit category functionality. Implemented automatic cursor placement at end of textbox text on focus. Window titles change between create and edit mode.
2025-05-12 | 1.25 | Item amount feature | Added Amount property to GroceryItem class. Implemented amount input field in AddItem XAML. Added amount binding and database integration. Implemented amount validation. Added to list display UI.
2025-05-13 | 0.75 | Checked item visual feedback | Implemented greyed-out and crossed-out styling for checked grocery items. Added DataTriggers for checked item appearance in MainWindow and ViewLists.
2025-05-14 | 3.75 | Favorite items system | Added IsFavorite, FavId and IsSelected properties to GroceryItem. Added Favorites ObservableCollection to StoreLayout. Created FavoriteItems database table. Implemented save/load/delete methods. Added favorite UI system to MainWindow. Added favorite selected ListBox with Checkboxes in CreateList.
2025-05-16 | 1.5 | Favorite items system completion and stability | Added message when no favorites exist for selected layout. Fixed crash when Add Favorites. Implemented favorite heart UI in CreateList. Prevented duplicate favorite additions to current list.
2025-05-18 | 1 | README documentation, licensing & bug fixes | Improved project README structure and documentation. Added MIT License. Fixed layout deletion bug caused by favorite item database references and implemented proper favorite cleanup when deleting layouts.
2025-05-19 | 0.5 | Documentation, screenshots & UI polish | Created sample data for demonstration and screenshots. Added application screenshots to README. Improved text wrapping behavior in AddItem window to prevent long names from being cut off.
2026-05-21 | 1.5 | Final code cleanup & polishing | Removed unused code and unnecessary comments from XAML and C# files. Added comments for important logic and database behavior. Performed final code cleanup, formatting, and overall project polishing before submission.
Total | 53